## Progress Planning and Tracking
Project Name: | Spotify Music Suggestions
Report Date:
[5 empty] | Milestone #1 | [7 empty] | Milestone #2 | [6 empty] | C-Day
Deliverable | Tasks | Complete% | Current Status Memo | Assigned To | 2023-01-12 | 2023-01-19 | 2023-01-26 | 2023-02-02 | 2023-02-09 | 2023-02-16 | 2023-02-23 | 2023-03-02 | 2023-03-09 | 2023-03-16 | 2023-03-23 | 2023-03-30 | 2023-04-06 | 2023-04-13 | 2023-04-20 | 2023-04-27
Requirements | Meet with group | 100% | Complete | All | 2023-01-12: 8; 2023-01-19: 8
| Assign roles | 0% |  | All | 2023-02-02: 2
| Define requirements |  |  | Mark, Vincent | 2023-01-26: 2; 2023-02-02: 2; 2023-02-09: 2
| Review requirements with group | 0% |  | All | 2023-02-02: 3; 2023-02-09: 1
Research | React-Native documentation | 0% |  | All | 2023-01-26: 4; 2023-02-02: 4
| Spotify API documentation | 0% |  | All | 2023-01-26: 4; 2023-02-02: 4
Project Design | Define tech required* | 0% |  | All | 2023-02-02: 2; 2023-02-09: 2
| Discussion of the flow of the app (ERD concept design) | 0% |  | Khemrind, Vincent | 2023-02-02: 2; 2023-02-09: 4
| Create UI concept of the flow of the app |  |  | Leiko, Vincent | 2023-02-02: 2; 2023-02-09: 4
| Access Spotify Database | 0% |  | Khemrind, Leiko | 2023-02-09: 4; 2023-02-16: 2
| Integrate with user / user data | 0% |  | Khemrind, Leiko | 2023-02-16: 6; 2023-02-23: 8
| Develop music recommendation algorithm | 0% |  | All | 2023-02-16: 5; 2023-02-23: 10; 2023-03-02: 10
| Update playlist following recommendations | 0% |  | Khemrind | 2023-02-23: 10; 2023-03-02: 10
| Develop working prototype | 0% |  | Khemrind, Leiko | 2023-02-23: 15; 2023-03-02: 15
| Test prototype | 0% |  | All | 2023-03-02: 4; 2023-03-09: 4
Development | Review prototype design | 0% |  | All | 2023-03-09: 2; 2023-03-16: 2; 2023-03-23: 2
| Rework requirements | 0% |  | All | 2023-03-23: 6; 2023-03-30: 6; 2023-04-06: 6; 2023-04-13: 6
| Document changes | 0% |  | Mark | 2023-04-13: 3; 2023-04-20: 4
| QA Testing | 0% |  | All | 2023-04-06: 5; 2023-04-13: 5; 2023-04-20: 5
Final report | Presentation preparation | 0% |  | Mark, Vincent | 2023-04-13: 4; 2023-04-20: 4; 2023-04-27: 3
| Website preparation | 0% |  | Mark, Vincent | 2023-04-20: 5; 2023-04-27: 6
| Final report submission to D2L and project owner | 0% |  | Mark, Vincent | bar: 2023-04-20 to 2023-04-27
|  |  | Total work hours | 239 | 8 | 8 | 10 | 21 | 17 | 13 | 43 | 39 | 6 | 2 | 8 | 6 | 11 | 18 | 19 | 10
* formally define how you will develop this project including source code management
Legend
Planned
Delayed
Number | Work: man hours